## MoSCoW Matrix
Library Management System – MoSCoW Prioritisation
Scoring: Impact (1-5) = value to users & stakeholders; Feasibility (1-5) = ease given time, budget, team. Priority Score = Impact x Feasibility (formula). Blue cells = judgement inputs you can change.
ID | Requirement | Description | Impact (1-5) | Feasibility (1-5) | Priority Score | MoSCoW Category | Impact Justification (Users & Stakeholders) | Feasibility Justification (Time / Budget / Resources) | Final Decision Rationale | Target Release
REQ-01 | Search books by title and author | Keyword search across catalogue by book title and author name. | 5 | 5 | 25 | Must Have | Every member and librarian uses it on every visit; without it the catalogue is unusable. | Standard database query / indexed search; low effort, no third-party cost, 1 developer, 1 sprint. | Highest value and lowest effort. Core function – system cannot launch without it. | Release 1 (MVP)
REQ-02 | Online book reservation system | Members reserve a book that is out/available and get a hold until pickup. | 5 | 4 | 20 | Must Have | Core library workflow; reduces queues and manual registers; directly serves members and librarians. | Needs reservation table, status rules, expiry logic; moderate effort, no external cost. | Essential to the library lifecycle (search > reserve > borrow). Needed for a usable MVP. | Release 1 (MVP)
REQ-03 | Email notifications for overdue books | Automatic emails on due-soon and overdue items. | 4 | 4 | 16 | Must Have | Protects library assets and fines revenue; reduces librarian manual follow-up; members avoid penalties. | Scheduled job + SMTP/SendGrid free tier; low-moderate effort and cost. | Overdue control is a core business need, and it is cheap to automate. Included in MVP. | Release 1 (MVP)
REQ-04 | Monthly borrowing reports for administrators | Auto-generated monthly report of borrowed books (exportable PDF/Excel). | 4 | 4 | 16 | Should Have | Administrators need it for stock and budget decisions, but the library can run without it at launch. | Aggregation queries + export library; moderate effort once borrowing data exists. | Important but depends on borrowing data from Must items. Can be delivered shortly after MVP. | Release 2
REQ-05 | User-friendly dashboard for librarians | Single screen showing issues, returns, overdue, reservations, quick actions. | 4 | 3 | 12 | Should Have | Improves librarian productivity and training time; high stakeholder satisfaction. | Needs UX design and several widgets; moderate effort. Basic admin screens cover MVP. | Valuable but MVP can use simple admin lists first; full dashboard follows. | Release 2
REQ-06 | QR code scanning for borrowing and returning | Scan book/member QR codes to issue and return books. | 4 | 3 | 12 | Should Have | Speeds up desk transactions and cuts data-entry errors. | Needs QR generation, label printing and camera/scanner integration; moderate effort and some hardware cost. | Big efficiency gain, but manual/ID entry works at launch. Schedule after core flows are stable. | Release 2
REQ-07 | Users can review and rate books | Star ratings and text reviews per book. | 3 | 4 | 12 | Could Have | Improves engagement and discovery but is not needed for lending operations. | Simple CRUD plus moderation; low effort. | Nice-to-have; add if time and budget remain after Must/Should items. | Release 3
REQ-08 | Multi-language support | UI available in multiple languages (e.g. English, Tamil, Hindi). | 3 | 3 | 9 | Could Have | Widens accessibility for diverse users; not critical if the primary user base shares one language. | Requires i18n framework from the start and translation effort; moderate cost. | Beneficial but not essential at launch. Build text with i18n keys so it can be added later cheaply. | Release 3
REQ-09 | Chatbot for user assistance | AI/FAQ chatbot answering member queries. | 2 | 2 | 4 | Won't Have (this time) | Convenient, but FAQs, search and librarian help cover the need. | High effort: NLP/AI service, training content, ongoing cost and maintenance. | Low impact for high cost. Deferred; revisit once usage data justifies it. | Backlog / Future
REQ-10 | Mobile app version of the system | Native iOS/Android app. | 4 | 1 | 4 | Won't Have (this time) | Useful for members, but a responsive website serves mobile users initially. | Very high effort: separate codebases, app-store process, extra team and budget. | Not feasible within current time/budget. Mitigation: make the web app mobile-responsive; plan app for a later phase. | Backlog / Future
Assumptions: small team (3-5 people), limited budget, ~3 releases; scores are team judgement and can be edited (blue cells). Category is chosen by judgement guided by Priority Score (>=16 Must, 12-15 Should, 9-11 Could, <9 Won't) with dependencies considered.

## Summary
MoSCoW Summary
Category | No. of Requirements | Share of Total | Requirements
Must Have | 3 | 30% | Search; Reservation; Overdue email alerts
Should Have | 3 | 30% | Monthly reports; Librarian dashboard; QR scanning
Could Have | 2 | 20% | Reviews & ratings; Multi-language
Won't Have (this time) | 2 | 20% | Chatbot; Mobile app (use responsive web)
Total | 10 | 100%

## Jira Import
Summary | Issue Type | Priority | Labels | Description | Epic Name / Parent
REQ-01 Search books by title and author | Story | Highest | Must | Keyword search across catalogue by book title and author name. ¦ Rationale: Highest value and lowest effort. Core function – system cannot launch without it. | Release 1 (MVP)
REQ-02 Online book reservation system | Story | Highest | Must | Members reserve a book that is out/available and get a hold until pickup. ¦ Rationale: Essential to the library lifecycle (search > reserve > borrow). Needed for a usable MVP. | Release 1 (MVP)
REQ-03 Email notifications for overdue books | Story | Highest | Must | Automatic emails on due-soon and overdue items. ¦ Rationale: Overdue control is a core business need, and it is cheap to automate. Included in MVP. | Release 1 (MVP)
REQ-04 Monthly borrowing reports for administrators | Story | High | Should | Auto-generated monthly report of borrowed books (exportable PDF/Excel). ¦ Rationale: Important but depends on borrowing data from Must items. Can be delivered shortly after MVP. | Release 2
REQ-05 User-friendly dashboard for librarians | Story | High | Should | Single screen showing issues, returns, overdue, reservations, quick actions. ¦ Rationale: Valuable but MVP can use simple admin lists first; full dashboard follows. | Release 2
REQ-06 QR code scanning for borrowing and returning | Story | High | Should | Scan book/member QR codes to issue and return books. ¦ Rationale: Big efficiency gain, but manual/ID entry works at launch. Schedule after core flows are stable. | Release 2
REQ-07 Users can review and rate books | Story | Medium | Could | Star ratings and text reviews per book. ¦ Rationale: Nice-to-have; add if time and budget remain after Must/Should items. | Release 3
REQ-08 Multi-language support | Story | Medium | Could | UI available in multiple languages (e.g. English, Tamil, Hindi). ¦ Rationale: Beneficial but not essential at launch. Build text with i18n keys so it can be added later cheaply. | Release 3
REQ-09 Chatbot for user assistance | Story | Low | Wont | AI/FAQ chatbot answering member queries. ¦ Rationale: Low impact for high cost. Deferred; revisit once usage data justifies it. | Backlog / Future
REQ-10 Mobile app version of the system | Story | Low | Wont | Native iOS/Android app. ¦ Rationale: Not feasible within current time/budget. Mitigation: make the web app mobile-responsive; plan app for a later phase. | Backlog / Future
Use: File > Save As CSV from this sheet, then import in Jira (see steps). Labels are Must / Should / Could / Wont (Jira labels cannot contain spaces or apostrophes).